## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Revisiting statistics concepts and Python libraries for ML | COULD HAVE | None | Anushka Bharadwaj | 3- Completed
S2 | S2 | US-001 | Project Goal Discussion | MUST HAVE | None | Anushka Bharadwaj | 3- Completed
S3 | S3 | US-001 | Introduction to RAG Model | MUST HAVE | None | Anushka Bharadwaj | 3- Completed
S4 | S4 | US-001 | Setting up the project requirements and neccessities | MUST HAVE | Text editor, Python, Groq API key, Libraries | Anushka Bharadwaj | 3- Completed
S5 | S5 | US-001 | Working with pdf files using RAG Model | MUST HAVE | Text editor, Python, Groq API key, Libraries | Anushka Bharadwaj | 3- Completed
S6 | S6 | US-001 | Working with csv files using RAG (Pandas AI Agent) | MUST HAVE | Text editor, Python, Groq API key, Libraries | Anushka Bharadwaj | 3- Completed
S7 | S7 | US-001 | Building Interface(GUI) | SHOULD HAVE | Streamlit | Anushka Bharadwaj | 3- Completed
S8 | S8 | US-001 | Git repository and doubt discussion | MUST HAVE | Git | Anushka Bharadwaj | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to RAG |  |  | Amidepuram Hemanthswamy | Others | 3- Completed | 3 | bar: Day 1 to Day 3
US-001 | TID-02 | Setting up the project requirements |  |  | Amidepuram Hemanthswamy | Coding | 3- Completed | 2 | bar: Day 4 to Day 5
US-001 | TID-03 | Working with pdf files using RAG |  |  | Amidepuram Hemanthswamy | Coding | 3- Completed | 3 | bar: Day 6 to Day 7
US-001 | TID-04 | Working with csv files using RAG (Pandas AI Agent) |  |  | Amidepuram Hemanthswamy | Coding | 3- Completed | 2 | bar: Day 8 to Day 9
US-001 | TID-05 | Building GUI |  |  | Amidepuram Hemanthswamy | Coding | 3- Completed | 2 | bar: Day 8; Day 10
US-001 | TID-06 | Git repository and doubt discussion |  |  | Amidepuram Hemanthswamy | Others | 3- Completed | 1 | bar: Day 11
US-001 | TID-07 | Project discussion |  |  | Amidepuram Hemanthswamy | Others | 3-Completed | 3 | bar: Day 12 to Day 14
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Standup Meeting
Sprint | Day | Impediments | Action Taken
Sprint-2 | Day-3 | Lack of clarity in project goals | Discussed with mentor
Sprint-3 | Day-4 | Doubts about RAG | Read about the topic
Sprint-4 | Day-5 | Issue in setting up the project | Updated Python version
Sprint-7 | Day-11 | Building and integrating GUI | Simplified the GUI and cleared confusion about requirements

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S2 | 2025-02-10 | 2025-02-18 | Amidepuram Hemanthswamy | Understand end goal at early stage itself | _ | Ask doubts when confused | Understood project goals completely
2 | S3 | 2025-02-19 | 2025-02-24 | Amidepuram Hemanthswamy | Read more about concepts | Procrastinating small tasks | Gain knowledge about topics | Learned about RAG
3 | S4 | 2025-02-25 | 2025-02-26 | Amidepuram Hemanthswamy | Keep tools and software updated | Downloading libraries/ softwares without checking in device first | Get started with work in time | Set up VS code for project and accessed Groq key
4 | S5 | 2025-02-27 | 2025-03-03 | Amidepuram Hemanthswamy | Follow systematic approach | Not dedicating enough time for tasks | Practice mentor's code first | Completed pdf based RAG
5 | S6 | 2025-03-04 | 2025-03-05 | Amidepuram Hemanthswamy | Follow systematic approach | Not dedicating enough time for tasks | Practice mentor's code first | Completed csv based RAG
6 | S7 | 2025-03-06 | 2025-03-07 | Amidepuram Hemanthswamy | Dedicate time to integrate GUI with backend | Proceed without reading documentation | Start with simple first draft | Integrated GUI with project